## 1. Consulting Firms
Republic of Tajikistan
Private Sector Competitiveness Project
PROCUREMENT PLAN - CONSULTING FIRMS - MARCH 2012- MARCH 2016
ПЛАН ЗАКУПОК КОНСУЛЬТАЦИОННЫХ УСЛУГ НА ПЕРИОД МАРТ 2012-МАРТ 2016
(Date of PP:11.03.2012; Update No.05.12.2012; Date of WB NOL: )
(Дата ПЗ: ________; Обновление № ______; Дата одобрения ВБ: ________)
Item № | Responsible Agencies | Component Reference as per PAD | Contract Ref. | Contract Description | Plan vs Actual | Estimated Cost (US$ equivalent) | Select. Method | WB Review (Prior/ Post) | Request for Exp. Of Interest | Draft RFP (incl. TOR, Short List) | WB No-objection to RFP (full package) | RFP Issued | Date of Proposal Submission | Tech. Evaluation Report (TER) | WB No-objection to TER | Combined Tech & Fin Eval. Report | Draft Final Contract | WB No-objection to Draft Contract | Date of Contract Signing | Date of Contract Completion | Remarks
№ Пункта | Ответственные агентства | Ссылка на компоненты согласно Документу об Оценке Проекта | № Контракта | Описание контракта | План и Факт | Бюджет (US$) | Метод отбора | Обзор Банка (предварит./последующ.) | Запрос на выраж. заинт | Проект ППП вкл ТЗ и КС | Одобрение Банка на полный пакет ППП | Выпуск ППП | Срок подачи предложений | Технический оценочный отчет (ТО) | Одобрение ВБ на ТО | Комбин. оцен. отчет | Проект финального контракта | Одобрение Банка на контракт | Подписание контракта | Завершение контракта | Примечания
Component 1: Strengthening the Business Environment (US$ 7.6 mln, out of which US$ 1.3 mln is expected from SECO)
1 | NBT | 1.3. Improving Financial Infratructure | PSC/QCBS1 | Strengthening the banking regulation and supervision functions of the NBT | Planned/План | 700000 | QCBS | Prior | 2012-12-20 | 2013-01-22 | 2013-01-26 | 2013-02-09 | 2013-03-06 | 2013-04-06 | 2013-04-20 | 2013-05-17 | 2013-06-08 | 2013-06-15 | 2013-06-30 | 2015-04-15
Actual/Факт
Component 2: Encouraging the Development of the Mining Industry (US$ 3.1 million).
2 | SCISPM, Geology Agency, Mininstry of Industry and Energy | 2.1. Improvement of the legal framework in the mining sector | PSC/QCBS2 | Improving legal, regulatory and fiscal framework for mining, including environmental and social studies | Planned/План | 450000 | QCBS | Prior | 2012-12-20 | 2013-01-22 | 2013-01-26 | 2013-02-09 | 2013-03-06 | 2013-04-06 | 2013-04-20 | 2013-05-17 | 2013-06-08 | 2013-06-15 | 2013-06-30 | 2014-03-22
Actual/Факт
3 | Geology Agency, Gortechnadzor, Ministry of Industry and Energy |  | PSC/CQS1 | Improving institutional framework for mining | Planned/План | 100000 | CQS | Prior | 2012-12-30 | 2013-01-30 | 2013-02-10 | 2013-02-20 | 2013-03-20 | 2013-04-07 | 2013-04-15 | 2013-05-10 | 2013-05-31 | 2013-06-10 | 2013-06-20 | 2014-06-20
Actual/Факт
4 | Geology Agency, Gortechnadzor, Ministry of Industry and Energy | 2.2. Development of a modern mining cadastre | PSC/QCBS3 | Training for capacity building of Government staff on implementation of mining laws and regulations | Planned/План | 400000 | QCBS | Prior | 2013-02-01 | 2013-02-21 | 2013-03-01 | 2013-03-08 | 2013-04-08 | 2013-05-08 | 2013-05-28 | 2013-06-28 | 2013-07-15 | 2013-07-25 | 2013-08-10 | 2014-08-10
Actual/Факт
5 | Geology Agency |  | PSC/QCBS4 | Design, development of and training in modern mining cadastre | Planned/План | 875000 | QCBS | Prior | 2013-02-01 | 2013-02-21 | 2013-03-01 | 2013-03-08 | 2013-04-08 | 2013-05-08 | 2013-05-28 | 2013-06-28 | 2013-07-15 | 2013-07-25 | 2013-08-10 | 2014-12-10
Actual/Факт
6 | Geology Agency | 2.3. Modernization of the geological survey function | PSC/QCBS5 | Design, development of and training in modern geological survey | Planned/План | 450000 | QCBS | Prior | 2013-02-01 | 2013-02-21 | 2013-03-01 | 2013-03-08 | 2013-04-08 | 2013-05-08 | 2013-05-28 | 2013-06-28 | 2013-07-15 | 2013-07-25 | 2013-08-10 | 2014-09-10
Actual/Факт
7 | Geology Agency, Gortechnadzor, Ministry of Industry and Energy | 2.4. Stakeholder outreach TA | PSC/QCBS6 | Workshops and public consultations | Planned/План | 450000 | QCBS | Prior | 2013-06-03 | 2013-07-03 | 2013-07-17 | 2013-07-31 | 2013-08-28 | 2013-09-25 | 2013-10-09 | 2013-10-30 | 2013-11-20 | 2013-11-27 | 2013-12-04 | 2014-12-04
Actual/Факт
8 | Geology Ageny, Gortechnadzor, Ministry of Industry and Energy, Committee for Environmental Protection and Nature | SESA | PSC/QSBS7 | Srategic environmental and social assessment | Planned/План | 100000 | Fixed Budget | Prior | 2012-12-15 | 2013-01-15 | 2013-02-05 | 2013-02-12 | 2013-03-12 | 2013-04-12 | 2013-04-30 | 2013-05-31 | 2013-06-21 | 2013-06-30 | 2013-07-10 | 2014-07-01
Actual/Факт
Component 3: Project Management (US$ 0.9 million, out of which US$ 0.3 million is expected from SECO)
9 | SCISPM | 3. Project Management | PSC/LCS1 | Project Audit | Planned/План | 60000 | LCS | Prior | 2012-11-03 | 2012-12-03 | 2012-12-17 | 2012-12-31 | 2013-01-28 | 2013-02-26 | 2013-03-09 | 2013-03-30 | 2013-04-20 | 2013-04-27 | 2013-05-06 | 2017-03-07
[5 empty] | Actual/Факт | 33805 |  |  | Block Audit of the Financial Statements of the World-Bank-funded 20 projects and Related Entity in the Republic of Tajikistan selected by SCI | [9 empty] | 2012-08-30 | 2017-08-30

## 2. Individual Consultants
Republic of Tajikistan
Private Sector Competitiveness Project
PROCUREMENT PLAN - INDIVIDUAL CONSULTANTS - MARCH 2012-MARCH 2016
ПЛАН ЗАКУПОК УСЛУГ индивидуала КОНСУЛЬТАНТОВ (по методу CQS - отбор по квалификации консультанта или индивидуала)
(Date of PP:11.03.2012; Update No.05.12.2012; Date of WB NOL: )
Item № | Responsible Agencies | Component Reference as per PAD | Contract Ref. | Contract Description | Plan vs Actual | Estimated Cost (US$ equivalent) | Firm or Ind. | Select. Method | WB Review (Prior/ Post) | Draft TOR | WB No-objection to TOR | Request for Exp. Of Interest | Evaluation report for Short list & RFP | WB No-objection to RFP/ Short list | RFP Issued (for CQS) | Proposal Submission | Draft Final Contract | WB No-objection to Draft Contract | Date of Contract Signing | Date of Contract Completion | Remarks
№ Пункта | Ответственные агентства | Ссылка на компоненты согласно Документу об Оценке Проекта | № Контракта | Описание контракта | План и Факт | Бюджет (US$) | Фирма или Индивидуал | Метод отбора | Обзор Банка (предварит./последующ.) | Проект ТЗ | Одобрение ВБ | Запрос на выраж. заинт | Оцен. отчет по краткому списку и ППП | Одобрение ВБ на ППП и краткий список | Выпуск ППП | Срок подачи предложений | Проект финального контракта | Одобрение ВБ на финальный контракт | Подписание контракта | Завершение контракта | Примечания
Component 1: Strengthening the Business Environment (US$ 7.6 mln, out of which US$ 1.3 mln from SECO)
1 | Tax Committee, Statistics, Pension Fund | 1.1. Completion of an online on-stop-shop for business registration | PSC/IC1 | Consultant to review and draft legal and regulatory acts for one-stop-shop for business registration and conduct capacity-building | Planned/План | 100000 | Ind. | IC | Prior | 2013-01-01 | 2013-01-15 | 2013-01-29 | 2013-02-28 | 2013-03-15 | n/a | n/a | 2013-03-31 | 2013-04-15 | 2013-04-30 | 2014-02-08
Actual/Факт
2 | Mayor's Office, Construction Agency, Office of the Chief Architect of Dushanbe, utilities companies | 1.2. Improving the construction permits framework | PSC/IC2 | Consultant to review and draft legal and regulatory acts for one-stop-shop for construction permits and conduct capacity-building | Planned/План | 200000 | Ind. | IC | Prior | 2013-01-01 | 2013-01-15 | 2013-01-29 | 2013-02-28 | 2013-03-15 | n/a | n/a | 2013-03-31 | 2013-04-15 | 2013-04-30 | 2014-02-08
[5 empty] | Actual/Факт | 0
3 | NBT/MOJ | 1.3. Improving financial infrastructure | PSC/IC3 | Legal expert to review the laws on creating and protecting the security interest and to assist in developing regulations governing the operation of the collateral registry | Planned/План | 100000 | Ind. | IC | Prior | 2013-01-01 | 2013-01-15 | 2013-01-29 | 2013-02-28 | 2013-03-15 | n/a | n/a | 2013-03-31 | 2013-04-15 | 2013-04-30 | 2014-02-08
Actual/Факт
4 | NBT/MOJ |  | PSC/IC4 | Legal expert on debt resolution | Planned/План | 100000 | Ind. | IC | Prior | 2013-01-01 | 2013-01-15 | 2013-01-29 | 2013-02-28 | 2013-03-15 | n/a | n/a | 2013-03-31 | 2013-04-15 | 2013-04-30 | 2014-02-08
Actual/Факт
5 | NBT |  | PSC/IC5 | TA (Consulting Services) for strengthening the regulation and oversight of the National Payments System | Planned/План | 200000 | Ind. | IC | Prior | 2013-02-15 | 2013-02-28 | 2013-03-19 | 2013-04-02 | 2013-04-16 | n/a | n/a | 2013-05-05 | 2013-05-15 | 2013-05-30 | 2014-05-30
Actual/Факт
6 | NBT |  | PSC/IC6 | IT specifications for Automated Transfer Sytem (ATS) and Central Securities Depository (CSD) | Planned/План | 50000 | Ind. | IC | Prior | 2013-02-15 | 2013-02-28 | 2013-03-19 | 2013-04-02 | 2013-04-16 | n/a | n/a | 2013-05-05 | 2013-05-15 | 2013-05-30 | 2014-05-30
Actual/Факт
7 | NBT |  | PSC/IC7 | IT specifications for upgrading NBT's ICT infrastructure | Planned/План | 50000 | Ind. | IC | Prior | 2013-09-05 | 2013-09-19 | 2013-10-03 | 2013-11-03 | 2013-11-17 | n/a | n/a | 2013-11-24 | 2013-12-01 | 2013-12-15 | 2015-02-15
Actual/Факт
Component 3: Project Management (US$ 0.9 million, out of which US$ 0.3 million is expected from SECO)
8 | SCISPM | 3. Project Management | PSC/IC10 | Financial Manager | Planned/План | 48000 | Ind. | IC | Prior | 2012-07-10 | 2012-07-24 | 2012-08-24 | 2012-09-07 | 2012-09-21 | n/a | n/a | 2012-09-28 | 2012-10-12 | 2012-10-26 | 2016-06-30
[5 empty] | Actual/Факт |  |  |  |  | 2012-07-10 | 2012-07-25 |  | 2012-08-17 |  |  |  | 2012-08-28 | 2012-08-31 | 2012-09-01 | 2012-12-31
9 | SCISPM |  | PSC/IC11 | Procurement Specialist | Planned/План | 48000 | Ind. | IC | Prior | 2012-12-10 | 2012-12-24 | 2013-01-24 | 2013-02-01 | 2013-02-10 | n/a | n/a | 2013-02-12 | 2013-02-15 | 2013-02-20 | 2016-06-30
Actual/Факт
10 | SCISPM |  | PSC/IC12 | Administrative Assistant/Communications Specialist | Planned/План | 33600 | Ind. | IC | Post | 2012-12-10 | 2012-12-24 | 2013-01-24 | 2013-02-01 | 2013-02-10 | n/a | n/a | 2013-02-12 | 2013-02-15 | 2013-02-20 | 2016-06-30
Actual/Факт
11 | SCISPM |  | PSC/IC13 | Technical Specialist/ Monitoring&Evaluation Spesialist | Planned/План | 48000 | Ind. | IC | Post | 2012-12-10 | 2012-12-24 | 2013-01-24 | 2013-02-01 | 2013-02-10 | n/a | n/a | 2013-02-12 | 2013-02-15 | 2013-02-20 | 2016-06-30
Actual/Факт
12 | SCISPM |  | PSC/IC14 | Administrative Assistant/Translator | Planned/План | 33600 | Ind. | IC | Post | 2012-12-10 | 2012-12-24 | 2013-01-24 | 2013-02-01 | 2013-02-10 | n/a | n/a | 2013-02-12 | 2013-02-15 | 2013-02-20 | 2016-06-30
Actual/Факт

## 3. Goods & Works
Republic of Tajikistan
Private Sector Competitiveness Project
PROCUREMENT PLAN - GOODS AND WORKS for March 2012 - March 2016
План закупок товаров и работ на период с марта 2012 по март 2016
(Date of PP:11.03.2012; Update No.05.12.2012; Date of WB NOL: )
(Дата ПЗ: ________; Обновление № ______; Дата одобрения ВБ: ________)
Item № | Responsible Agencies | Component Reference as per PAD | Contract Ref. № | Contract Description | Plan vs Actual | Estimated Cost (US$ equivalent) | Procu. Method | WB Review (Prior/ Post) | Date of Draft BD to WB | WB No-objection to BD | Date of Invitation to Bids | Date of Bid Opening | Bid Evaluation Report | WB No-objection to Contract Award | Date of Contract Signing | Date of Contract Completion | Remarks
№ Пункта | Ответственные агентства | Ссылка на компоненты согласно Документу об Оценке Проекта | № Контракта | Описание контракта | План и Факт | Бюджет (US$) | Метод закупок | Обзор Банка (предварит./последующ.) | Конкурс. документ на рассмотрение ВБ | Одобрение ВБ на конкурс. док. | Объявление | Вскрытие конкурсных заявок | Оценочный отчет | Одобрение ВБ на присуждение контракта | Подписание контракта | Завершение контракта | Примечания
Component 1: Strengthening the Business Environment (US$ 7.6 mln, out of which US$ 1.3 mln from SECO)
1 | Tax Committee, Statistics, Pension Fund | 1.1. Completion of an online on-stop-shop for business registration | PSC/ICB1 | Design and implementation of the one-stop shop for business registration, which includes procurement of hardware, software and training firms for equipping of each registry at three agencies and training the relevant staff | Plan/План | 500000 | ICB | Prior | 2013-06-01 | 2013-06-15 | 2013-06-29 | 2013-08-30 | 2013-09-28 | 2013-10-12 | 2013-11-02 | 2014-11-02
Actual/Факт
2 | Mayor's Office, Construction Agency, Office of the Chief Architect of Dushanbe, utilities companies | 1.2. Improving the construction permits framework | PSC/ICB2 | Design and implementation of the single window for constuction permits, which includes procurement of hardware and software for establishing a pilot single window for construction permits in Dushanbe city | Plan/План | 600000 | ICB | Prior | 2013-04-10 | 2013-04-24 | 2013-05-08 | 2013-07-09 | 2013-08-09 | 2013-08-23 | 2013-09-13 | 2014-09-13
Actual/Факт
3 | NBT/MOJ | 1.3. Improving financial infrastructure | PSC/ICB3 | Design and implementation of the collateral registry, which includes procurement of hardware, software and training firms for equipping of the collateral registry and training the relevant staff | Plan/План | 300000 | ICB | Prior | 2013-06-01 | 2013-06-15 | 2013-06-29 | 2013-08-30 | 2013-09-28 | 2013-10-12 | 2013-11-02 | 2014-11-02
Actual/Факт
4 | NBT |  | PSC/ICB4 | Procurement of a modern ATS and CSD to improve the payments infrastructure | Plan/План | 1950000 | ICB | Prior | 2013-07-01 | 2013-07-15 | 2013-07-29 | 2013-09-29 | 2013-10-28 | 2013-11-11 | 2013-12-02 | 2014-12-02
Actual/Факт
5 | NBT |  | PSC/ICB5 | Procurement of systems for upgrading the NBT's ICT infrastructure | Plan/План | 1450000 | ICB | Prior | 2013-10-14 | 2013-10-28 | 2013-11-11 | 2014-01-12 | 2014-02-10 | 2014-02-24 | 2014-03-17 | 2015-03-17
Actual/Факт
Component 2: Encouraging the Development of the Mining Industry (US$ 3.1 million).
6 | Geology Agency | 2.2. Development of a modern mining cadastre | PSC/NCB1 | Procurement of software and hardware for developing an automated mining cadastre, including IT requirements | Plan/План | 125000 | NCB | Prior | 2013-01-01 | 2013-01-15 | 2013-01-29 | 2013-02-15 | 2013-03-15 | 2013-03-22 | 2013-03-31 | 2013-12-04
Actual/Факт
7 | Geology Agency | 2.3. Modernization of the geological survey function | PSC/NCB2 | Procurement of ICT infrastructure for for the Geological Survey Function including IT requirements | Plan/План | 150000 | NCB | Post | 2013-01-01 | 2013-01-15 | 2013-01-29 | 2013-03-30 | 2013-04-30 | 2013-05-13 | 2013-06-04 | 2014-12-04
Actual/Факт
8 | Geology Agency |  | PSC/ICB6 | Procurement of Field Survey Equipment | Plan/План | 150000 | NCB | Prior | 2013-01-01 | 2013-01-15 | 2013-01-29 | 2013-03-30 | 2013-04-30 | 2013-05-13 | 2013-06-04 | 2014-12-04
Actual/Факт
Component 3: Project Management (US$ 0.9 million, out of which US$ 0.3 million is expected from SECO)
9 | SCISPM | 3. Project Management | PSC/SH1 | Computers for PMU | Plan/План | 30000 | SH | Prior | 2012-12-10 | 2012-12-24 | 2012-12-30 | 2013-01-13 | 2013-01-27 | 2013-02-05 | 2013-02-10 | 2013-03-10
Actual/Факт
10 | SCISPM |  | PSC/SH2 | Furniture for PMU | Plan/План | 30000 | SH | Post | n/a | n/a | 2012-12-06 | 2012-12-20 | 2012-12-30 | n/a | 2013-01-07 | 2013-02-07
Actual/Факт
11 | SCISPM |  | PSC/SH3 | Accounting software for PMU | Plan/План | 15000 | SH | Post | n/a | n/a | 2012-08-14 | 2012-08-28 | 2012-08-28 | n/a | 2012-08-30 | 2013-08-30
[5 empty] | Actual/Факт | 7310 |  |  |  |  | 2012-08-14 | 2012-08-28 | 2012-08-28 | n/a | 2012-08-30 | 2013-08-30
12 | SCISPM |  | PSC/SH4 | Car for PMU | Plan/План | 25000 | SH | Post | n/a | n/a | 2012-12-06 | 2012-12-20 | 2012-12-30 | n/a | 2013-01-07 | 2013-02-07
Actual/Факт