|  |
| --- |
| 90737 v2  **Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 09/14/2012 |

|  |  |
| --- | --- |
| **1. Basic Information** | |
| Project ID & Name | P084302: Sindh Water Sector Improvement Project |
| Country | Pakistan |
| Task Team Leader | Masood Ahmad |
| Sector Manager/Director | Simeon Kacou Ehui |
| Country Director | Rachid Benmessaoud |
| Original Board Approval Date | 09/18/2007 |
| Original Closing Date: | 04/30/2013 |
| Current Closing Date | 02/28/2015 |
| Proposed Closing Date [if applicable] | 02/28/2015 |
| EA Category | A-Full Assessment |
| Revised EA Category | A-Full Assessment-Full Assessment |
| EA Completion Date | 09/30/2004 |
| Revised EA Completion Date | 09/30/2004 |

|  |  |  |
| --- | --- | --- |
| **2. Revised Financing Plan (US$m)** | | |
| **Source** | **Original** | **Revised** |
| BORR | 24.80 | 24.80 |
| IDA | 150.20 | 150.20 |
| **Total** | 175.00 | 175.00 |

|  |  |  |
| --- | --- | --- |
| **3. Borrower** | | |
| **Organization** | **Department** | **Location** |
| Government of Pakistan |  | Pakistan |
| Government of Sindh............ |  | Pakistan |

|  |  |  |
| --- | --- | --- |
| **4. Implementing Agency** | | |
| **Organization** | **Department** | **Location** |

|  |  |  |
| --- | --- | --- |
| **5. Disbursement Estimates (US$m)** | | |
| **Actual amount disbursed as of 09/16/2014** **64.18** | | |
| **Fiscal Year** | **Annual** | **Cumulative** |
| 2010 | 0.00 | 64.18 |
|  | **Total** | **64.18** |

|  |  |
| --- | --- |
| **6. Policy Exceptions and Safeguard Policies** | |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes**  **Original/Current Project Development Objectives/Outcomes** |
| The overarching project objective is to improve the efficiency and effectiveness of irrigation water distribution in three AWBs (Ghotlu, Nara and Left Bank), particularly with respect to measures of reliability, equity and user satisfaction. This would be achieved by: (a) deepening and broadening the institutional reforms that are already underway in Sindh; (b) improving the irrigation system in a systematic way covering key hydraulic infrastructure, main and branch canals, and distributaries and minors; and (c) enhancing long-term sustainability o f irrigation system through participatory irrigation management and developing institutions for improving operation and maintenance of the system and cost recovery. The improved water management would lead to increased agricultural production, employment and incomes over some about 1.8 million ha or more than 30 percent o f the irrigated area in Sindh, and one of the poorest regions o f the country. |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|  |