|  |
| --- |
| **Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 11/30/2012 |

|  |
| --- |
| **1. Basic Information** |
| Project ID & Name | P096823: LOCAL SERVICES DELIVERY |
| Country | Serbia |
| Task Team Leader | Christoph Kurowski |
| Sector Manager/Director | Roberta V. Gatti |
| Country Director | Jane Armitage |
| Original Board Approval Date | 03/18/2008 |
| Original Closing Date: | 12/31/2012 |
| Current Closing Date | 12/31/2012 |
| Proposed Closing Date [if applicable] | 12/31/2013 |
| EA Category | B-Partial Assessment |
| Revised EA Category | B-Partial Assessment-Partial Assessment |
| EA Completion Date | 02/21/2008 |
| Revised EA Completion Date |  |

|  |
| --- |
| **2. Revised Financing Plan (US$m)** |
| **Source** | **Original** | **Revised** |
|  BORR | 0.00 | 0.00 |
|  IBRD | 46.40 | 46.40 |
|  **Total** | 46.40 | 46.40 |

|  |
| --- |
| **3. Borrower** |
| **Organization** | **Department** | **Location** |
|  Ministry of Finance, Republic of Serbia |  | Serbia |

|  |
| --- |
| **4. Implementing Agency** |
| **Organization** | **Department** | **Location** |
|  Ministry of Labor and Social Policy |  | Serbia |
|  Ministry of Health |  | Serbia |
|  Ministry of Education and Science |  | Serbia |

|  |
| --- |
| **5. Disbursement Estimates (US$m)** |
| **Actual amount disbursed as of 11/30/2012** **24.09** |
| **Fiscal Year** | **Annual** | **Cumulative** |
|  2012 | 0.00 | 24.09 |
|  2013 | 11.00 | 35.09 |
|  2014 | 11.31 | 46.40 |
|   | **Total** | **46.40** |

|  |
| --- |
| **6. Policy Exceptions and Safeguard Policies** |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes****Original/Current Project Development Objectives/Outcomes** |
| The project will help to increase the capacity of institutional actors and Beneficiaries in order to improve access to and the efficiency, equity and quality of local delivery of health, education and social protection services, in a decentralizing environment.  |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|   |