## sepa 1
Project name: Second Solid Waste Management - Federation |  | New Activities
Loan: 7629-FD |  | Modified Activities
Procurement Plan Version: 2012-2 |  | Canceled Activities
Status: Approved |  | Activities without Modification
Date of Last Change of Status: 18/07/2012
Category Works: Activities ShowHide
Description | Reference # | Federation | E/A | Amount in u$s | No Objection Documents | Publication / Invitation | Bid Opening | Evaluation of Bids | No Objection to Evaluation Report | Signing of Contract | Total days of Process | End of Contract (Completed) | Comment
(between Bid Opening and Signing of Contract)
P.P. - Executing Agency: 2012-2-FEDERATION - FEDERATION
Method: SH (Shopping)
Renovation of offices for PMU ( painting, flooring, toilets etc) | SWMP2-FD-6-CP-O-BA-SSWMP-4540-SH-010-W-11 | _Bosnia&Herzegovina |  | 45,000.00 | N/A | 18/10/12 | 02/11/12 | 02/12/12 | N/A | 09/12/12 | 37 | 09/05/13
Expected
Post Review
| 359557 |  | Actual
Elaborate of investigation works on the landfill side Pakline- Tomislavgrad | SWMP2-FD-26-CP-O-SH-024-S-11/PMU | Hercegovina |  | 45,000.00 | N/A | 04/06/12 | 19/06/12 | 19/07/12 | N/A | 26/07/12 | 37 | 31/08/12 | update contract end date. 12/07/2012 15:34
Ongoing Activity
Post Review
| 359560 |  | Actual |  |  | 18/06/12 | 06/07/12
P.P. - Executing Agency: 2012-2-LIVNO - LIVNO
Method: NCB (National Competitive Bidding)
Construction of entrance – exit area infrastructure and contruction of recycling plateau | SWMP2-FD-34-LPN-O-BA-SSWMP-7629-NCB-031-W-1 | Livno |  | 400,000.00 | N/A | 01/01/13 | 01/02/13 | 01/03/13 | N/A | 01/04/13 | 59 | 19/09/13 | Update of the % of Bank Loan Amount (90) 20/06/2012 05:43
works | Expected
Post Review
| 362858 |  | Actual
Construction of disposal cells | SWMP2-FD-35-LPN-O-BA-SSWMP-7629-NCB-032-W-1 | Livno |  | 550,000.00 | 02/01/13 | 03/01/13 | 02/02/13 | 03/02/13 | 04/02/13 | 05/02/13 | 3 | 19/12/13 | Update of the % of Bank Loan Amount (90) 20/06/2012 05:49
Expected
Prior Review
| 362918 |  | Actual
Method: SH (Shopping)
Construction of fence | SWMP2-FD-36-CP-O-BA-SSWMP-7629-SH-033-W-12 | Livno |  | 100,000.00 | N/A | 15/09/12 | 30/09/12 | 15/10/12 | N/A | 16/10/12 | 16 | 07/12/12 | Re-estimation of dates 10/07/2012 07:09
Expected
Post Review
| 362921 |  | Actual
P.P. - Executing Agency: 2012-2-MOSTAR - MOSTAR
Method: NCB (National Competitive Bidding)
Construction of the additional objects of the entry-exit zone on Uborak landfill Mostar | SWMP2-FD-3-LPN-O-BA-SSWMP-4540-NCB003-W-10 | _Bosnia&Herzegovina |  | 800,000.00 | 21/05/12 | 25/05/12 | 25/06/12 | 23/07/12 | 31/07/12 | 01/08/12 | 37 | 01/06/13
Ongoing Activity
Prior Review
| 359575 |  | Actual |  | 31/05/12 | 05/06/12 | 04/07/12
Method: SH (Shopping)
Supply of vehicle for PIT Mostar | SWMP2-FD-29-CP-O-BA-SSWMP-4540-SH-029-G-12 | Hercegovina |  | 15,000.00 | N/A | 15/01/12 | 17/01/12 | 18/01/12 | N/A | 23/01/12 | 6 | 20/03/12
Contract Completed
Post Review
| 359571 |  | Actual | 20,140.00 |  | 12/01/12 | 19/01/12 | 20/01/12 |  | 23/01/12 | 4 | 01/02/12
Method: ICB (International Competitive Bidding)
Construction of the entry-exit zone on “Uborak” landfill Mostar | SWMP2-FD-1-LPI-O-BA-SSWMP-4540-ICB-001-W-1 | _Bosnia&Herzegovina |  | 1,500,000.00 | 15/06/10 | 22/06/10 | 03/08/10 | 02/09/10 | 09/09/10 | 19/09/10 | 47 | 19/09/11
Contract Completed
Prior Review
| 359572 |  | Actual | 1,021,823.25 | 18/06/10 | 21/06/10 | 04/08/10 | 20/08/10 | 25/08/10 | 23/09/10 | 50 | 23/09/11
Construction of the disposal cell - phase I | SWMP2-FD-2-LPI-O-BA-SSWMP-4540-ICB-002-W-1 | _Bosnia&Herzegovina |  | 1,600,000.00 | 14/09/10 | 21/09/10 | 02/11/10 | 02/12/10 | 09/12/10 | 19/12/10 | 47 | 19/12/10
Contract Completed
Prior Review
| 359576 |  | Actual | 1,260,506.00 | 24/08/10 | 20/09/10 | 26/11/10 | 17/12/10 | 22/12/10 | 30/12/10 | 34 | 31/12/11
P.P. - Executing Agency: 2012-2-ZENICA - ZENICA
Method: NCB (National Competitive Bidding)
Preparation works for closure of dump " Sidje" Zenica | SWMP2-FD-5-LPN-O-BA-SSWMP-7629-NCB-005-W-1 | _Bosnia&Herzegovina |  | 800,000.00 | 08/09/12 | 11/09/12 | 11/10/12 | 10/12/12 | 17/12/12 | 24/12/12 | 74 | 01/04/13
Expected
Prior Review
| 359580 |  | Actual
Method: ICB (International Competitive Bidding)
Preparation for Closure, including Landslide Repair on “Sidje” Solid Waste Disposal Site at Zenica | SWMP2-FD-4-LPI-O-BA-SSWMP-7629-ICB-004-W-1 | _Bosnia&Herzegovina |  | 1,328,000.00 | 28/08/10 | 31/08/10 | 12/10/10 | 22/10/10 | 29/10/10 | 15/11/10 | 34 | 09/08/12
Contract under execution
Prior Review
| 359581 |  | Actual | 1,174,897.72 | 22/08/10 | 08/09/10 | 20/10/10 | 04/02/11 | 04/02/11 | 09/03/11 | 140
Category Goods: Activities ShowHide
Description | Reference # | Federation | E/A | Amount in u$s | No Objection Documents | Publication / Invitation | Bid Opening | Evaluation of Bids | No Objection to Evaluation Report | Signing of Contract | Total days of Process | End of Contract (Completed) | Comment
(between Bid Opening and Signing of Contract)
P.P. - Executing Agency: 2012-2-FEDERATION - FEDERATION
Method: SH (Shopping)
Supply of IT and office equipment ( PC, notebook, printers, faxes, etc ) | SWMP2-FD-7-CP-B-BA-SSWMP-4540-SH-006-G-11 | Sarajevo |  | 40,000.00 | N/A | 10/09/11 | 25/09/11 | 09/10/11 | N/A | 16/10/11 | 21 | 16/01/12
Contract Completed
Post Review
| 359555 |  | Actual | 13,779.26 |  | 13/09/11 | 27/09/11 | 25/10/11 |  | 28/10/11 | 31 | 02/02/12
Supply of vehicle | SWMP2-FD-10-CP-B-BA-SSWMP-4540-SH-009-G-11 | Sarajevo |  | 24,000.00 | N/A | 17/02/13 | 04/03/13 | 18/03/13 | N/A | 25/03/13 | 21 | 25/05/13
Expected
Post Review
| 359556 |  | Actual
Supply of Telephone equipment and cameras | SWMP2-FD-8-CP-B-BA-SSWMP-4540-SH-007-G-11 | Sarajevo |  | 16,000.00 | N/A | 02/12/12 | 09/12/12 | 10/12/12 | N/A | 11/12/12 | 2 | 11/03/13
Expected
Post Review
| 359562 |  | Actual
Office furniture ( shelfs, tables, chairs... | SWMP2-FD-9-CP-B-BA-SSWMP-4540-SH-008-G-11 | Sarajevo |  | 20,000.00 | N/A | 04/12/12 | 19/12/12 | 02/01/13 | N/A | 09/01/13 | 21 | 09/03/13
Expected
Post Review
| 359565 |  | Actual
Category Consultants - Firms: Activities ShowHide
Description | Reference # | Federation | E/A | Amount in u$s | Request for Proposal (RFP) and Short List | No Objection to RFP and Short List | Invitation for RFP | Bid Opening | Technical Evaluation | No Objection to Technical Evaluation | Final Evaluation and Negotiation | No Objection to Contract | Signing of Contract | Total days of Process | End of Contract (Completed) | Comment
(between Bid Opening and Signing of Contract)
P.P. - Executing Agency: 2012-2-FEDERATION - FEDERATION
Method: DC (Direct contracting)
Upgrading of financial software | SWMP2-FD-16-CD-CF-BA-SSWMP-4540-SSS-021-S-1 | Sarajevo |  | 4,500.00 | N/A | N/A | 18/11/10 | 18/11/10 | N/A | N/A | 20/11/10 | 25/11/10 | 01/12/10 | 13 | 10/01/11
Contract Completed
Prior Review
| 359566 |  | Actual | 3,900.00 |  |  | 24/11/10 | 24/11/10 |  |  | 30/11/10 | 17/12/10 | 23/12/10 | 29 | 31/01/11
Method: QCBS (Quality and Cost Based Selection)
Public campaign | SWMP2-FD-14-SBCC-CF-BA-SSWMP-7629-QCBS-016-S- | Sarajevo |  | 200,000.00 | 07/03/12 | 14/03/12 | 21/03/12 | 20/04/12 | 20/05/12 | 27/05/12 | 26/08/12 | 03/09/12 | 10/09/12 | 143 | 10/09/13 | update dates 12/07/2012 15:37
Coofinancing with SIDA | Ongoing Activity
Prior Review
| 359558 |  | Actual |  | 05/06/12 | 06/06/12 | 12/06/12
Strategic study for hazardous waste management in FBIH | SWMP2-FD-15-SBCC-CF-BA-SSWMP-7629-QCBS-017-S- | Sarajevo |  | 220,000.00 | 31/03/13 | 07/04/13 | 14/04/13 | 14/05/13 | 13/06/13 | 20/06/13 | 20/07/13 | 27/07/13 | 03/08/13 | 81 | 03/02/14
Expected
Prior Review
| 359568 |  | Actual
Method: CQS (Selection based on consultants qualifications)
Feasibility Study for landfill Pakline - Tomislavgrad | SWMP2-FD-28-SCC-CF-4540-CQ-026_S-11/TG | Hercegovina |  | 95,000.00 | 14/06/12 | N/A | 15/06/12 | 30/06/12 | 15/07/12 | N/A | 22/07/12 | N/A | 29/07/12 | 29 | 29/11/12
Contract under execution
Post Review
| 359563 |  | Actual | 98,145.23 | 23/05/12 |  | 01/06/12 | 15/06/12 |  |  | 18/06/12 |  | 18/06/12 | 3
P.P. - Executing Agency: 2012-2-LIVNO - LIVNO
Method: CQS (Selection based on consultants qualifications)
Final design for sanitary landfill Livno | SWMP2-FD-37-SCC-CF-BA-SSWMP-7629-CQS-034-S-1 | Livno |  | 100,000.00 | 02/10/12 | N/A | 09/10/12 | 08/11/12 | 22/11/12 | N/A | 23/11/12 | N/A | 30/11/12 | 22 | 30/01/13 | Re-estimation of dates 11/07/2012 09:00
Expected
Post Review
| 362922 |  | Actual
Supervision services of all works on | SWMP2-FD-38-SCC-CF-BA-SSWMP-7629-CQS-035-S-1 | Livno |  | 60,000.00 | 02/09/12 | N/A | 09/09/12 | 09/10/12 | 23/10/12 | N/A | 24/10/12 | N/A | 31/10/12 | 22 | 31/10/13 | Re-estimation of dates 11/07/2012 09:10
Expected
Post Review
| 362924 |  | Actual
P.P. - Executing Agency: 2012-2-MOSTAR - MOSTAR
Method: CQS (Selection based on consultants qualifications)
Changes and amendments of the main project | SWMP2-FD-12-SCC-CF-BA-SSWMP-4540-CQ-012-S-10 | _Bosnia&Herzegovina |  | 25,000.00 | 30/10/11 | N/A | 28/04/12 | 09/05/12 | 30/11/11 | N/A | 30/11/11 | N/A | 15/05/12 | 6 | 15/08/12 | Update of the % of Bank Loan Amount (90) 20/06/2012 06:07
Contract under execution
Post Review
| 359573 |  | Actual | 32,370.00 | 13/02/12 |  | 26/04/12 | 09/05/12 |  |  | 15/05/12 |  | 21/05/12 | 12
Supervision of the Construction of the entry-exit zone and of the construction of the disposal cell on “Uborak” landfill Mostar | SWMP2-FD-11-SCC-CF-BA-SSWMP-4540-CQ-011-S-10 | _Bosnia&Herzegovina |  | 69,000.00 | 15/10/10 | 25/10/10 | 12/11/10 | 12/11/10 | N/A | N/A | 15/11/10 | 01/12/10 | 04/12/10 | 22 | 04/12/11
Contract Completed
Prior Review
| 359574 |  | Actual | 74,745.00 | 17/12/10 | 21/12/10 | 22/12/10 | 30/12/10 | N/A | N/A | 28/01/11 | 08/02/11 | 10/02/11 | 42 | 08/03/12
Supervision of execution of works on additional facilities on entrance zone at Uborak landfill Mostar | SWMP2-FD-33-SCC-CF-BA-SSWMP-CQ-030-S-12-MO | Hercegovina |  | 40,000.00 | 12/07/12 | N/A | 19/07/12 | 18/08/12 | 19/08/12 | N/A | 26/08/12 | N/A | 27/08/12 | 9 | 26/10/12 | Update of the % of Bank Loan Amount (90) 20/06/2012 06:19
Mostar | Expected
Post Review
| 359583 |  | Actual
P.P. - Executing Agency: 2012-2-ZENICA - ZENICA
Method: CQS (Selection based on consultants qualifications)
Nostrification of Main Design for closure of dump site Sidje, Zenica | SWMP2-FD-23-SCC-CF-BA-SSWMP-7629-CQ-028-S-11 | Zenica-Doboj |  | 6,200.00 | 03/09/11 | N/A | 04/09/11 | 04/10/11 | 05/10/11 | N/A | 06/10/11 | N/A | 07/10/11 | 3 | 19/12/11
Contract Completed
Post Review
| 359577 |  | Actual | 6,600.00 | 14/09/11 |  | 27/10/11 | 04/11/11 | 09/11/11 |  | 17/11/11 |  | 17/11/11 | 13 | 13/02/12
Supervision services on preparation works for closure of wild dumps ite Sidje Zenica | SWMP2-FD-22-SCC-CF-BA-SSWMP-7629-CQ-027-S11/ | Zenica-Doboj |  | 46,200.00 | 15/09/12 | N/A | 22/09/12 | 22/10/12 | 21/11/12 | N/A | 28/11/12 | N/A | 05/12/12 | 44 | 05/04/13
Expected
Post Review
| 359578 |  | Actual
Supervision of closure preparation and landslide repair works on Sidje Solid Waste Disposal Site at Zenica | SWMP2-FD-13-SCC-CF-BA-SSWMP-7629-CQ-014-S-10 | _Bosnia&Herzegovina |  | 33,200.00 | 09/02/11 | 16/02/11 | 23/02/11 | 25/03/11 | 24/04/11 | 01/05/11 | 02/05/11 | 09/05/11 | 16/05/11 | 52 | 29/08/12
Contract under execution
Prior Review
| 359582 |  | Actual | 52,782.00 | 24/03/11 | 31/03/11 | 01/04/11 | 14/04/11 | N/A | N/A | 18/04/11 | 18/04/11 | 29/04/11 | 15
Category Consultants - Individuals: Activities ShowHide
Description | Reference # | Federation | E/A | Amount in u$s | No Objection to the TOR | Signing of Contract | Total days of Process | End Date of Activity | Comment
P.P. - Executing Agency: 2012-2-FEDERATION - FEDERATION
Method: 3CV (3CV)
Accauntant | SWMP2-FD-21-3CV-CI-BA-SSWMP-4540-IC-020-S-10 | _Bosnia&Herzegovina |  | 37,000.00 | N/A | 01/10/10 |  | 28/02/14
Contract under execution
Post Review
| 359553 |  | Actual | 27,268.00 |  | 01/12/10
Preparation of TOR for public Campaign | SWMP2-FD-24-3CV-CI-IC-022-S-11/PMU | Sarajevo |  | 5,000.00 | N/A | 28/03/11 |  | 24/05/11 | insert the date when the contract was terminated. 12/07/2012 15:42
Contract Completed
Post Review
| 359561 |  | Actual | 4,074.00 |  | 24/01/11 |  | 26/07/11
Preparation of TOR for Strategic Study for hazardus waste | SWMP2-FD-25-3CV-CI-IC-023-S-11/PMU | Sarajevo |  | 5,000.00 | N/A | 01/12/12 |  | 01/02/13
Expected
Post Review
| 359564 |  | Actual
Preaparation of TOR for Public Campaign | SWMP2-FD-32-3CV-CI-4540-IC-022-S-11/PMU-2 | Sarajevo |  | 5,000.00 | N/A | 01/12/10 |  | 01/03/11
The procurement proces was renewed | Contract Completed
Post Review
| 359567 |  | Actual | 8,500.00 | 20/12/10 | 20/10/11 |  | 20/12/11
Preparation of TOR for feasibility Study - Tomislavgrad | SWMP2-FD-27-3CV-CI-IC-025-S-11/TG | Hercegovina |  | 10,000.00 | N/A | 15/05/12 |  | 05/06/12 | Activity canceled 11/07/2012 07:36
Activity canceled
Post Review
| 359569 |  | Actual
Method: DC (Direct contracting)
Financial Manager | SWMP2-FD-19-CD-CI-BA-SSWMP-4540-IC-018-S-10 | _Bosnia&Herzegovina |  | 93,000.00 | 01/09/10 | 01/10/10 |  | 28/02/14
Contract under execution
Prior Review
| 359554 |  | Actual | 48,566.00 | 08/12/10 | 08/12/10
Administrative asistant | SWMP2-FD-20-CD-CI-BA-SSWMP-4540-IC-019-S-10 | _Bosnia&Herzegovina |  | 44,000.00 | 01/09/10 | 01/10/10 |  | 28/02/14
Contract under execution
Prior Review
| 359559 |  | Actual | 27,268.00 | 08/12/10 | 08/12/10
P.P. - Executing Agency: 2012-2-LIVNO - LIVNO
Method: 3CV (3CV)
TOR for main design | SWMP2-FD-39-3CV-CI-BA-SSWMP-7629-IC-036-S-12 | Livno |  | 5,000.00 | N/A | 30/07/12 |  | 03/09/12 | Update of the % of Bank Loan Amount (90) 20/06/2012 05:30
Expected
Post Review
| 362966 |  | Actual
Technical support for PIT | SWMP2-FD-40-3CV-CI-BA-SSWMP-7629-IC-037-S-12 | Livno |  | 5,000.00 | N/A | 30/07/12 |  | 01/08/12 | Update of the % of Bank Loan Amount (90) 20/06/2012 05:31
Expected
Post Review
| 362967 |  | Actual
Procurement officer | SWMP2-FD-41-3CV-CI-BA-SSWMP-7629-IC-038-S-12 | Livno |  | 30,000.00 | N/A | 30/07/12 |  | 01/12/14 | Update of the % of Bank Loan Amount (90) 20/06/2012 05:32
Expected
Post Review
| 362968 |  | Actual
P.P. - Executing Agency: 2012-2-MOSTAR - MOSTAR
Method: 3CV (3CV)
Technical consultant for solid waste management | SWMP2-FD-17-3CV-CI-BA-SSWMP-4540-IC-013-S-10 | _Bosnia&Herzegovina |  | 15,000.00 | N/A | 23/11/11 |  | 23/02/12
Contract Completed
Post Review
| 359570 |  | Actual | 13,787.00 | 13/09/11 | 23/11/11 |  | 23/02/12
P.P. - Executing Agency: 2012-2-ZENICA - ZENICA
Method: 3CV (3CV)
Technical consultant for solid waste management | SWMP2-FD-18-3CV-CI-BA-SSWMP-7629-IC-015-S-10 | _Bosnia&Herzegovina |  | 20,000.00 | N/A | 03/11/11 |  | 11/07/13
Contract under execution
Post Review
| 359579 |  | Actual | 12,143.00 | 29/09/11 | 09/01/12