## Goods & Works
Republic of Tajikistan
MINISTRY OF HEALTH
Institutional Development Fund Grant (IDF Grant)
PROCUREMENT PLAN - GOODS
(Date of PP: December 14, 2012; Update No.December 18,2012; Date of WB NOL: ___________ 2012)
No. | Package Number | Description | Plan vs. Actual | Estimated Cost (US$ equivalent) | Procu. Method | WB Review (Prior/ Post) | Date of Draft BD to WB | WB No-objection to BD | Date of Invitation to Bids | Date of Bid Opening | Bid Evaluation Report | WB No-objection to Contract Award | Date of Contract Signing | Date of Contract Completion | Award of contract
GOODS
Component 1. Capacity Development for Implementation of Health Financing Reforms
1 | MOH/IDF/SHG/013/001 | Stationery for the local consultants to be hired under IDF grant | Plan | 6000 | SHG | Post | n/a | n/a | Mar-13 | Mar-13 | Apr-13 | n/a | Apr-13 | May-13
Actual
2 | MOH/IDF/SHG/013/002 | Procurement of computers and office equipment for the local consultants to be hired under IDF grant | Plan | 30000 | SHG | Post | n/a | n/a | Feb-13 | Feb-13 | Mar-13 | n/a | Mar-13 | May-13
Actual
Total for Component 1 |  |  | Plan | 36000
Actual
Total for GOODs |  |  | Plan | 36000

## Consultants
Republic of Tajikistan
MINISTRY OF HEALTH
Institutional Development Fund Grant (IDF Grant)
PROCUREMENT PLAN - CONSULTANTING SERVICES
(Date of PP: December 14, 2012; Update No.December 18,2012; Date of WB NOL: ___________ 2012)
No | Package Number | Description | Plan vs. Actual | Estimated Cost (US$ equivalent) | Firm or Ind. | Select. Method | WB Review (Prior/ Post) | Request for Exp. Of Interest | Draft RFP (incl. TOR, Short List) | WB No-objection to RFP (full package) | RFP Issued | Date of Proposal Submission | Tech. Evaluation Report (TER) | WB No-objection to TER | Combined Tech & Fin Eval. Report | Draft Final Contract | WB No-objection to Draft Contract | Date of Contract Signing | Date of Contract Completion | Award of Contract
Component 1. Capacity Development for Implementation of Health Financing Reforms
1 | MOH/IDF/CQS/013/001 | International TA to Health Financing & Policy Assessment/Development of the capacity Building Action Plan at the level of the key units of MOH and Sughd/Khatlon OHD | Plan | 150000 | Firm | CQS | Prior | Feb-13 | Feb-13 | Feb-13(Bank's NOL to TOR) | Mar-13 | Mar-13 | Mar-13 | Mar-13 | N/A | Apr-13 | Apr-13 | Apr-13 | Apr-16
Actual
2 | MOH/IDF/IIC/013/001 | International TA to Development of Training Program and Design on Health Financing Best Practices and Monitoring for key MOH and Sughd/Khatlon OHD staff | Plan | 50000 | ind | IC | Prior | Feb-13 | N/A | Feb-13(Bank's NOL to TOR) | Mar-13 | Mar-13 | Mar-13 | Mar-13 | N/A | Apr-13 | Apr-13 | Apr-13 | Apr-16
Actual
3 | MOH/IDF/LIC/013/001 | Local TA to Health Financing & Policy Assessment at the level of the key units of MOH | Plan | 12000 | ind | IC | Post | Feb-13 | N/A | Jan-13(Bank's NOL to TOR) | N/A | N/A | Mar-13 | N/A | N/A | Mar-13 | N/A | Mar-13 | Mar-16
Actual
4 | MOH/IDF/LIC/013/002 | Local TA to Health Financing & Policy Assessment at the level of the key units of Sughd OHD | Plan | 11400 | ind | IC | Post | Feb-13 | N/A | Jan-13(Bank's NOL to TOR) | N/A | N/A | Mar-13 | N/A | N/A | Mar-13 | N/A | Mar-13 | Mar-16
Actual
5 | MOH/IDF/LIC/013/003 | Local TA to Development of the Capacity Building Action Plan at the level of the key units of MOH | Plan | 12000 | ind | IC | Post | Feb-13 | N/A | Jan-13(Bank's NOL to TOR) | N/A | N/A | Mar-13 | N/A | N/A | Mar-13 | N/A | Mar-13 | Mar-16
Actual
6 | MOH/IDF/LIC/013/004 | Local TA to Development of the Capacity Building Action Plan at the level of the key units of Sughd OHD | Plan | 11400 | ind | IC | Post | Feb-13 | N/A | Jan-13(Bank's NOL to TOR) | N/A | N/A | Mar-13 | N/A | N/A | Mar-13 | N/A | Mar-13 | Mar-16
Actual
7 | MOH/IDF/LIC/013/005 | Local Health Economics and Financial Management Consultant at the level of MOH | Plan | 12000 | ind | IC | Post | Feb-13 | N/A | Jan-13(Bank's NOL to TOR) | N/A | N/A | Mar-13 | N/A | N/A | Mar-13 | N/A | Mar-13 | Mar-16
Actual
8 | MOH/IDF/LIC/013/006 | Local Health Economics and Financial Management Consultant at the level of Sughd OHD | Plan | 11400 | ind | IC | Post | Feb-13 | N/A | Jan-13(Bank's NOL to TOR) | N/A | N/A | Mar-13 | N/A | N/A | Mar-13 | N/A | Mar-13 | Mar-16
Actual
9 | MOH/IDF/LIC/013/007 | Local Health Economics and Financial Management Consultant at the level of Khatlon OHD | Plan | 11000 | ind | IC | Post | Feb-13 | N/A | Jan-13(Bank's NOL to TOR) | N/A | N/A | Mar-13 | N/A | N/A | Mar-13 | N/A | Mar-13 | Mar-16
Actual
10 | MOH/IDF/LIC/013/008 | Local Health Finance and Organizational Reforms Consultant at the level of Khatlon OHD | Plan | 11000 | ind | IC | Post | Feb-13 | N/A | Jan-13(Bank's NOL to TOR) | N/A | N/A | Mar-13 | N/A | N/A | Mar-13 | N/A | Mar-13 | Mar-16
Actual
11 | MOH/IDF/LIC/013/009 | Local HMIS Consultant at the level of Khatlon OHD | Plan | 11000 | ind | IC | Post | Feb-13 | N/A | Jan-13(Bank's NOL to TOR) | N/A | N/A | Mar-13 | N/A | N/A | Mar-13 | N/A | Mar-13 | Mar-16
Actual
12 | MOH/IDF/LIC/013/010 | Local HMIS Consultant at the level of Sughd OHD | Plan | 11000 | ind | IC | Post | Feb-13 | N/A | Jan-13(Bank's NOL to TOR) | N/A | N/A | Mar-13 | N/A | N/A | Mar-13 | N/A | Mar-13 | Mar-16
Actual
Total for Component 1 |  |  | Plan | 314200
Actual
Component 2. Audit of the IDF Grant
1 | As difined by the selection agency | Project audit | Plan | 15000 | Firm | LCS | Prior | Selection and the contracting will be done by the State Investment Committee | [10 empty] | May-16
Actual
Total for Component 2 |  |  | Plan | 15000
Actual
Total for SERVICES |  |  | Plan | 329200
Actual

## Training
Republic of Tajikistan
MINISTRY OF HEALTH
Institutional Development Fund Grant (IDF Grant)
TRAINING PLAN (INCL. WORKSHOPS AND SEMINARS)
(Date of PP: December 14, 2012; Update No.December 18,2012; Date of WB NOL: ___________ 2012)
№ | Description | Plan vs. Actual | WB Review (Prior/ Post) | Estimated Cost (US$ equivalent) | Sending of the training budget, program and participants' list for Bank's review and NOL | Bank's NOL to conduct training | Start of training | Training completion
Component 1. Capacity Development for Implementation of Health Financing Reforms
1 | Technical Workshops on Health Financing Best Practices and Monitoring for MOH, MOF and Sughd/Khatlon OHD's key staff (totally four workshops on the quarterly basis) | plan | Training program & budget prior review | 60000 | May-13 | May-13 | June-13 | June-14
actual
2 | Training Tour on the Issues of Health Organizational and Financing Reforms for MOH, MOF and Sughd/ Khatlon OHD's Key Staff | plan | Training program & budget prior review | 30000 | May-13 | May-13 | June-13 | Sep-13
actual
3 | Training Tour on the Issues of Health Financing Best Practices and Monitoring for MOH, MOF and Sughd/Khatlon OHD's Key Staff | plan | Training program & budget prior review | 30000 | May-13 | May-13 | June-13 | Sep-13
actual
TOTAL FOR TRAINING |  | plan |  | 120000
actual

## Operational costs
Republic of Tajikistan
MINISTRY OF HEALTH
Institutional Development Fund Grant (IDF Grant)
OPERATING COSTS
(Date of PP: December 14, 2012; Update No.__________; Date of WB NOL: ___________ 2012)
№ | Description | Time spent | Time unit | Unit cost | Total estimated costs (US$ equivalent) | Start date | Completion date
Component 2. Audit of the IDF Grant and other operational activities
1 | Bank charges | 12 | month | 300 | 3600 | Feb-13 | Mar-14
2 | Advertising | 3 | times | 200 | 600 | Feb-13 | May-13
3 | DHL Services | 6 | times | 100 | 600 | Feb-13 | Feb-14
TOTALLY FOR OPERATIONAL COSTS | Операционные непредвиденные |  |  |  | 4800

## TOTALLY
Total planned costs
Expenditure category | Total amount (US$ equivalent) | %
Goods | 36000 | 7.347%
Consulting services | 329200 | 67.18%
Training/(workshops, seminars, tours) | 120000 | 24.49%
Operational costs | 4800 | 0.9796%
TOTALLY | 490000 | 100%