# Procurement Plan

# IDA CRISS RESPONSE WINDOW RESOURCES TO THE REPUBLIC OF KENYA FOR A HEALTH SECTOR SUPPORT PROJECT

## General

1. 	Project information:

Country: 								Kenya

CREDIT No.  							4771-KE
Project ID No.  							P074091

Project Implementing Agency (PIA):			Kenya Medical Supplies Agency (KEMSA)

2.      Bank’s approval Date of the procurement Plan [Original	: 30th November 2011; Revision 1- 21st November 2012.

- Date of General Procurement Notice: 28th September 2010

- Period covered by this procurement plan: 12 months

##### II. Goods and Works and non-consulting services.

- Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement: [Thresholds for applicable procurement methods (not limited to the list below) will be determined by the Procurement Specialist /Procurement Accredited Staff based on the assessment of the implementing agency’s capacity.]

|  | Procurement Method | Prior Review Threshold | Comments |
| --- | --- | --- | --- |
| 1. | ICB and LIB (Goods) | >$ 500,000 |  |
| 2. | NCB (Goods) | >$80000 - < $500,000 | Post review |
| 3. | ICB (Works) | N/A |  |
| 4. | NCB (Works) | N/A |  |
| 5. | ICB (Non-Consultant Services) | N/A |  |
|  | [Add other methods if necessary] |  |  |

2.	Pre-qualification :   NOT APPLICABLE

3.	Proposed Procedures for CDD Components (as per paragraph. 3.17 of the Guidelines: Procurement under IBRD Loans and IDA Credits dated May 2004 revised October 2006 and May 2010)

- Reference to (if any) Project Operational/Procurement Manual: Procurement under IBRD Loans and IDA Credits dated May 2004 revised October 2006 and May 2010

- Any Other Special Procurement Arrangements: NOT APPLICABLE

##### Procurement Packages with Methods and Time Schedule

| Ref. No. | Contract (Description) | Proc Method | Prequalification (yes/no) | Domestic Preference (yes/no) | IDA Review | Submit/Open bids | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Nutritional Supplements |  |  |  |  |  |  |  |
| 1 | KEMSA/KHSSP-CRW-OIT-01/2012-2013 | Multivitamin & Mineral Supplements | ICB | Yes | ICB | Prior | 8-Feb-13 |  |
| B | ANTI TB DRUGS |  |  |  |  |  |  |
| 1 | FIRST LINE ANTI TB DRUGS |  | ICB | No | Yes | Prior | 19-Jul-12 |  |
| 2 | SECOND LINE ANTI TB DRUGS |  | ICB | No | Yes | Prior | 8-Feb-13 |  |
| C | EMMS- PHARMACEUTICAL AND NON PHARMACEUTICALS |  |  |  |  |  |  |
| 1 | KEMSA/KHSSP-CRW-OIT-02/2012-2013 | Supply of Pharmaceuticals (Tablets - General) | ICB | No | Yes | Prior | 8-Feb-13 |  |
| 2 | KEMSA/KHSSP-CRW-OIT-03/2012-2013 | Supply of Pharmaceuticals (Tablet/Capsules (Anti Infectives) | ICB | No | Yes | Prior | 15-Feb-13 |  |
| 3 | KEMSA/KHSSP-CRW-OIT-04/2012-2013 | Supply of Pharmaceuticals (Syrups/Suspension) | ICB | No | Yes | Prior | 15-Feb-13 |  |
| 4 | KEMSA/KHSSP-CRW-OIT-05/2012-2013 | Supply of Pharmaceuticals (Injectables (Antibiotics) | ICB | No | Yes | Prior | 15-Feb-13 |  |
| 5 | KEMSA/KHSSP-CRW-OIT-06/2012-2013 | Supply of Pharmaceuticals (Injectables (General) | ICB | No | Yes | Prior | 15-Feb-13 |  |
| 6 | KEMSA/KHSSP-CRW-OIT-07/2012-2013 | Supply of Pharmaceuticals ( IV Infusions) | NCB | No | Yes | Post | 22-Feb-13 |  |
| 7 | KEMSA/KHSSP-CRW-OIT-08/2012-2013 | Supply of Pharmaceuticals (Disinfectants and Antiseptics) | ICB | No | Yes | Prior | 22-Feb-13 |  |
| 8 | KEMSA/KHSSP-CRW-OIT-09/2012-2013 | Supply of Pharmaceuticals (Ointment/Creams/Lotion/Drops/Pessaries/Inhalers(External Application) | ICB | No | Yes | Prior | 22-Feb-13 |  |
| 9 | KEMSA/KHSSP-CRW-OIT-10/2012-2013 | Supply of Non Pharmaceuticals (Loose) | ICB | No | Yes | Prior | 8-Feb-13 |  |
| 10 | KEMSA/KHSSP-CRW-OIT-11/2012-2013 | Supply of Pharmaceutical Packaging Materials | NCB | No | Yes | Post | 22-Feb-13 |  |
| D | EMMS FOR EMERGENCY RESPONSE LEVEL 4-5 |  |  |  |  |  |  |
| 1 | EMMS | Supply of Pharmaceuticals ( Loose) | ICB | No | Yes | Prior | 27-Aug-12 | Tender under evaluation |

##### III. Selection of Consultants

NOT APPLICABLE

- Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:

|  | Selection Method | Prior Review Threshold | Comments |
| --- | --- | --- | --- |
| 1. | Competitive Methods (Firms) |  |  |
| 2. | Single Source (Firms) |  |  |
|  | [Add specific methods if necessary] |  |  |

2. 	Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $_______equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

3.	Any Other Special Selection Arrangements: [including advance procurement and retroactive financing, if applicable]

4.	Consultancy Assignments with Selection Methods and Time Schedule

| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Description of Assignment | Estimated Cost | Selection Method | Review by Bank (Prior / Post) | Expected Proposals Submission Date | Comments |

##### IV. Implementing Agency Capacity Building Activities  with Time Schedule

1.	In this section the agreed Capacity Building Activities (some items could be from CPAR recommendation)  are listed with time schedule

| No. | Expected outcome / Activity Description | Estimated Cost | Estimated Duration | Start Date | Comments |
| --- | --- | --- | --- | --- | --- |

# Text boxes

74831