## PROCUREMENT PLAN FOR GOODS/WORKS              	                                                					  Draft

## COMPONENT-C (Original) / 3 (Restructured)   Strengthening Flood management Capacity                                                                        Plan (GOS/WKS)					                                                     BIHAR KOSI FLOOD RECOVERY PROJECT

WB LOAN/ CREDIT No 4802 IN					                             16 Dec, 2013

Implementing Agency – Water Resources Department, Govt. of Bihar

|  | SL No. | Package No. | Description of Works/Goods | Estimated Cost (Rs. in Mill-ions) | Method of Procurement ( ICB/ NCB ) | Review by Bank (Prior or Post ) | Estimate Prepared & Sanctioned (Date and Value) | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date)** | Bids | Contract Award decided (Date/ Value/ Currency) | Bank’s No Objection to Contract Award (Date)** | Contract Signed (Date/ Value/Currency) | Contract No. | Name of Contractor/ Nationality & ZIP Code | Contract completion date/period | Expenditure incurred to Date(Rs. in Mill-ions) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | Invitation (Date) | Opened on (Date) |  |  |  |  |  |  |  |  |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| PP | 1 | 2.0b.1 | Field stations to set up automated measuring network | 104.175 | ICB | Prior |  |  |  |  |  | 31.03.11 |  |  |  |  | 30.11.12 |  | This activity will constitute Real Time Data Acquisition System(RTDAS) |
| R |  | 2.0b.1 |  | 104.175 | ICB | Prior | 15.12.13 | 05.01.14 | 20.01.14 | 25.01.14 | 07.03.14 | 31.03.14 | 07.04.14 | 15.04.14 |  |  | 18 months |  |  |
| A |  | 2.0b.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PP | 2 | 3.0a | Roads Development on Western Kosi Embankment | 231.5 | NCB | Post | - | - | - | - | - | 30.11.10 | - | - | - | - | 31.07.11 |  | Activity 3.0a is renamed as Strengthening of Road on Western Kosi Embankment from 15.0 km to 23.0 km |
| R |  | 3.0a. |  | 224.55 | NCB | Post | 21.05.12 ,30.08.12 (Tech) 21.05.12 (Adm) | 21.11.12 | 14.02.12 | 01.10.12-02.11.12 | 03.11.12 | 23.03.13/ INR 184.68 million | 20.02.13 | 23.03.13 INR 184677854.76 | SBD-02/12-13 | M/sHardev Construction Pvt.Ltd, Deoghar, Jharkhand | 18 months |  |  |
| A |  | 3.0a |  | 224.55 | NCB | Post | 21.05.12, 30.08.12 (Tech) 21.05.12 (Adm) | 21.11.12 | 14.02.12 | 01.10.12-02.11.12 | 03.11.12 | 23.03.13/ INR 184.68 million | 20.02.13 | 23.03.13 INR 184677854.76 | SBD-02/12-13 | M/sHardev Construction Pvt.Ltd, Deoghar, Jharkhand |  | 30.07 |  |
| PP | 3 | 3.0b.1 | Pilot strengthening works- | 81.025 | NCB | Several contracts, 1st contract for Prior review | - | - | - | - | - | 30.11.10 | - | - | - | - | 31.03.12 |  | Activity 3.0b.1 is renamed as Restoration of Sanjay Dhar |
| R |  | 3.0b.1 |  | 25.542 | NCB |  | 27.09.12 ( Admin) 03.11.12 (Tech) | 31.01.13 | 06.03.13 | 15.03.13 | 09.05.13 | 06.09.13 | - | 15.10.13 INR18139080 | 1 SBD/ 13-14- | M/sHardev Construction Pvt.Ltd, Deoghar, Jharkhand | 12 months |  |  |
| A |  | 3.0b.1 |  | 25.542 | NCB |  | 27.09.12 ( Admin) 03.11.12 (Tech) | 31.01.13 | 06.03.13 | 15.03.13 | 09.05.13 | 06.09.13 |  | 15.10.13 INR18139080 | 1 SBD/ 13-14- | M/sHardev Construction Pvt.Ltd, Deoghar, Jharkhand |  |  |  |
|  | SL No. | Package No. | Description of Works/Goods | Estimated Cost (Rs. in Mill-ions) | Method of Procurement ( ICB/ NCB ) | Review by Bank (Prior or Post ) | Estimate Prepared & Sanctioned (Date and Value) | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date)** | Bids | Contract Award decided (Date/ Value/ Currency) | Bank’s No Objection to Contract Award (Date)** | Contract Signed (Date/ Value/Currency) | Contract No. | Name of Contractor/ Nationality & ZIP Code | Contract completion date/period | Expenditure incurred toDate(Rs. in Millions) | Remarks |
|  |  |  |  |  |  |  |  |  |  | Invitation (D ate) | Opened on (Date) |  |  |  |  |  |  |  |  |
| PP | 4 | 3.0b.2 | Pilot strengthening works | 81.025 | NCB | Several contracts, 1st contract for Prior review | - | - | - | - | - | 30.11.10 |  |  |  |  | 31.03.12 |  | Activity 3.0b.2 is renamed as Restoration of Bochaha Dhar |
| R |  | 3.0b.2 |  | 50.288 | NCB |  | 27.09.12 ( Admin) 03.11.12 (Tech) | 31.01.13 | 06.03.13 | 15.03.13 | 09.05.13 | 06.09.13 | - | 15.10.13 INR38019587 | 2SBD/13-14- | M/sHardev Construction Pvt. Ltd, | 12 months |  |  |
| A |  | 3.0b.2 |  | 50.288 | NCB |  | 27.09.12 ( Admin) 03.11.12 (Tech) | 31.01.13 | 06.03.13 | 15.03.13 | 09.05.13 | 06.09.13 |  | 15.10.13 INR38019587 | 2SBD/13-14- | M/sHardev Construction Pvt.Ltd, |  |  |  |
| PP | 5 | 3.0b.3 | Pilot strengthening works | 81.025 | NCB |  | - | - | - | - | - | 30.11.10 | - |  |  |  | 31.03.12 |  | Activity 3.0b.3 is renamed as Restoration of Haiyya Dhar |
| R |  | 3.0b.3 |  | 42.46 | NCB |  | 27.09.12 ( Admin) 03.11.12 (Tech) | 31.01.13 | 06.03.13 | 15.03.13 | 09.05.13 | 06.09.13 | - | 15.10.13 INR29271892 | 3SBD/13-14 | - | 12 months |  |  |
| A |  | 3.0b.3 |  | 42.46 | NCB |  | 27.09.12 ( Admin) 03.11.12 (Tech) | 31.01.13 | 06.03.13 | 15.03.13 | 09.05.13 | 06.09.13 | - | 15.10.13 INR29271892 | 3SBD/13-14 | M/s Rajbir Construction P. Ltd |  |  |  |
| PP | 6 | 3.0b.4 | Pilot strengthening works - | 81.025 | NCB |  | - | - | - | - | - | 30.11.10 | - |  |  |  | 31.03.12 |  | Activity 3.0b.4 is not identified. |
| R |  | - |  | - |  |  | - | - | - | - | - | - | - | - | - | - |  |  |  |
| A |  | - | - | - |  |  | - | - | - | - | - | - | - | - | - | - |  |  |  |
| PP | 7 |  |  | - |  |  | - | - | - | - | - | - | - | - | - | - |  |  | 1.Activities 3.0c.1 & 3.0c.2 are new additions in BKFRP (restructured) |
| R |  | 3.0c.1 | Revetment work with reno mattresses and gabion mattresses of Eastern Kosi Embankment, spurs and river edge between 78.00 Km and 84.00 Km. | 1400 | NCB | Prior | 10.11.13 | 28.11.13 | 13.12.13 | 16.12.14 | 14.01.14 | 21.01.14 | 25.01.14 | 31.01.14 | - | - | 15 months |  |  |
| A |  |  | - | - |  |  | 25.11.13 | - | - | - | - | - | - | - | - | - |  |  |  |
|  | SL No. | Package No. | Description of Works/Goods | Estimated Cost (Rs. in Mill-ions) | Method of Procurement ( ICB/ NCB ) | Review by Bank (Prior or Post ) | Estimate Prepared & Sanctioned (Date and Value) | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Documen(Date)** | Bids | Contract Award decided (Date/ Value/ Currency | Bank’s No Objection to Contract Award (Date)** | Contract Signed (Date/ Value/Currency) | Contract No. | Name of Contractor/ Nationality & ZIP Code | Contract completion date/period | Expenditure incurred toDate(Rs. in Millions) | Remarks |
|  |  |  |  |  |  |  |  |  |  | Invitation (Date) | Opened on (Date) |  |  |  |  |  |  |  |  |
| PP | 8 |  |  | - |  |  | - | - | - |  |  | - | - | - | - | - |  |  | Activity3.0c.2 is proposed to be fast forwarded and initiated in BKFRP(Kosi I) and the rest balance work to be completed in BKBDP (Kosi II) |
| R |  | 3.0c.2 | Revetment work with reno mattresses and gabion mattresses of Eastern Kosi Embankment, spurs and river edge between 0.00 Km and. 28.02 Km | 3583.1 | NCB | Prior | 25.11.13 | 06.12.13 | 13.12.13 | 16.12.14 | 14.01.14 | 21.01.14 | 25.01.14 | 31.01.14 | - | - | 15 months |  |  |
| A |  |  |  | - |  |  | - | - | - | - | - | - | - | - | - | - |  |  |  |
| PP | 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | New Introduction for BKFRP |
| R |  | 5.0 | Oracle11G for Data base Management | 4.0 | DC | Post |  | 25.12.2013 | 04.01.2014 |  |  | 10.03.14 | 25.03.14 | 02.04.14 |  |  | 3 months |  |  |
| A |  |  |  | - |  |  | - | - | - | - | - | - | - | - | - | - |  |  |  |
| TOTAL (Original Proc. Plan) | 659.775 |  |  |
| TOTAL (Restructured Proc. Plan) ‘R’ | 5434.116 |  |  |

| Asstt Dir FMISC, WRD | Dy Dir FMISC, WRD | Joint Dir. FMISC, WRD | In Charge PIU, WRD |
| --- | --- | --- | --- |

PP: Original Procurement Plan- 28 July, 10; (1 USD=46.13 INR)

R:  Proposed Procurement Plan (Restructured); (1 USD=60.00 INR)

A: Actual, NCB: National Competitive Bidding, ICB: International Competitive Bidding

PP: Target dates agreed as per Procurement Plan             R: revision 1,2 etc.          A: actual dates         WBR No.: World Bank Reference Number                      ** Applicable in case of ‘Prior Review’ by Bank.

Note: For Column 5, state ICB/NCB/Direct Contracting/Shopping as appropriate.  For Column Nos. 6 to 19, fill the information for all the three elements i.e.       PP, R and A, as applicable, against each contract.

# Text boxes

86523 v1