## Pro Plan SPMU , DPMU & PFT W.G
Procurement Plan from 1st Aug 2013 to 31st July 2014 (Civil Works and Goods)
S.No. | Package No. | Description Works/Goods | Procurement Agency | Estimated Cost (Rs. in Lacs) | Method of Procurement | Design/Invitation completed (Date) | Prior Review/Post Review | Estimate Prepared & Sanctioned (Date & Value) | Preparation of Bid Document (Date) | Bank's No Objection to Bidding Document (Date)** | Bids |  | Contract Award decided (Date/Value/Currency) | Bank's No Objection on to Contract Award | Contract Signed (Date/Value/Currency) | Name of Contractor/Nationality & Zip Code | **WB R No. | Date of Completion of Contract | Expenditure incurred to Date | Remarks
[11 empty] | Invitation (Date) | Opened On (Date)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
SPMU
| W-1 | Civil Works | SPMU | 30
1 | W-1(a) | Office upgradation | SPMU | 15 | Shopping | 30.11.2014 | Post | 15.12.2013 | 30.12.2013 | NA | 01.01.2014 | 16.01.2014 | 30.01.2014 | NA
2 | W-1(b) | Office Refurbishment (Cubicles and Attachment) | SPMU | 10 | Shopping | 30.10.2013 | Post | 15.11.2013 | 30.11.2013 | NA | 01.12.2013 | 16.12.2013 | 20.12.2013 | NA
3 | W-1(c) | Misc items (e.g. Doors, windows, frames etc.) | SPMU | 5 | Shopping | 30.10.2013 | Post | 15.11.2013 | 30.11.2013 | NA | 01.12.2013 | 16.12.2013 | 20.12.2013 | NA
| G-1 | IT/MIS |  | 4.45
4 | G-1(a) | Photo Copier-1 | SPMU | 1.7 | Shopping | 01.01.2014 | Post | 15.01.2014 | 30.01.2014 | NA | 01.02.2014 | 16.02.2014 | 20.02.2014 | NA
5 | G-1(b) | Tablet-5 | SPMU | 2 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
6 | G-1(c) | Printers-2 | SPMU | 0.25 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
7 | G-1(d) | Mobile Handset-5 | SPMU | 0.5 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-2 | Furniture & Fixtures |  | 20.35
8 | G-2(a) | Office Tables-10 | SPMU | 2.5 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
9 | G-2(b) | Chair Executive Meeting-20 | SPMU | 6 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
10 | G-2(c) | Director Table-2 | SPMU | 0.8 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
11 | G-2(d) | Computer Table-15 | SPMU | 1 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
12 | G-2(e) | Visitor Chair-30 | SPMU | 4.5 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
13 | G-2(f) | File Cabinet-10 | SPMU | 0.75 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
14 | G-2(g) | File Rakes-30 | SPMU | 3 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
15 | G-2(h) | Book Self with Glass-2 | SPMU | 0.6 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
16 | G-2(i) | Small Almaries-15 | SPMU | 1.2 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-3 | Other Office Equipments |  | 6.34
17 | G-3(a) | Purchase of K-YAN-1 | SPMU | 0.89 | Single Source | 29.07.2013 | Prior | 29.07.2013 & 0.89 | NA | 06.08.2013 | NA | NA | 07.08.2013 | NA | 07.08.2013 & 0.89 | M/s IL&FS Education & Technology Services Ltd, Jaipur |  | 07.09.2013
18 | G-3(b) | Fan-10 | SPMU | 0.25 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
19 | G-3(c) | Coolers-10 | SPMU | 0.6 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
20 | G-3(d) | Tublight-50 | SPMU | 0.2 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
21 | G-3(e) | Digital Camera-1 | SPMU | 0.15 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
22 | G-3(f) | Air Conditioner-10 | SPMU | 4 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
23 | G-3(g) | Coffee/Tea Machine-1 | SPMU | 0.25 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | Others Item |  | 102.3
24 | G-4 | Purchases of Car-1 | SPMU | 8 | DGS&D | 01.11.2013 | Post | 15.10.2013 | 25.10.2013 | NA | NA | NA | 30.11.2013 | NA
25 | G-5 | Printing of SHG books and other material for community | SPMU | 50 | NCB | 01.10.2013 | Prior | 15.10.2013
26 | G-5(a) | Printing of Record Keeping books for SHGs for 18 Districts -2500 sets | SPMU | 10 | Shopping | 01.10.2013 | Post | 15.10.2013 | 20.10.2013 | NA | 25.10.2013 | 15.11.2013 | 20.12.2013 | NA
27 | G-5(b) | Printing of Record Keeping books for SHGs for 18 Districts -3000 sets | SPMU | 12 | Shopping | 01.10.2013 | Post | 15.10.2013 | 20.10.2013 | NA | 25.10.2013 | 15.11.2013 | 20.12.2013 | NA
28 | G-5(c) | Printing of Record Keeping books for CDOs for 18 Districts-300 sets | SPMU | 8 | Shopping | 01.10.2013 | Post | 15.10.2013 | 20.10.2013 | NA | 25.10.2013 | 15.11.2013 | 20.12.2013 | NA
29 | G-5(d) | Purchase of Training books for SHGs | SPMU | 2.3 | Direct Contracting | 01.10.2013 | Prior
30 | G-5(e) | Printing of IEC Material | SPMU | 12 | Shopping
|  | SPMU TOTAL Civil Works |  | 30
|  | SPMU IT/MIS/Other Office Equipments |  | 133.44
|  | TOTAL SPMU Works/Goods |  | 163.44
DPMU's
| G-6 | DPMU Baran
| G-6(a) | Furniture and Fixtures | DPMU | 2.55 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-6(b) | Other Office equipments | DPMU | 2.55 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-6(c) | IT/MIS Equipments/K-YAN | DPMU | 2.57 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-6(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 2 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-6(e) | Other office equipments for 4 PFT offices | DPMU | 2.4 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT BARAN |  | 12.07
| G-7 | DPMU Churu
| G-7(a) | Furniture and Fixtures | DPMU | 1 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-7(b) | Other Office equipments | DPMU | 2 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-7(c) | IT/MIS Equipments/K-YAN | DPMU | 1.77 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-7(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 2.64 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-7(e) | Other office equipments for 4 PFT offices | DPMU | 1.46 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Churu |  | 8.87
| G-8 | DPMU Tonk
| G-8(a) | Furniture and Fixtures | DPMU | 2.73 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-8(b) | Other Office equipments | DPMU | 1.82 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-8(c) | IT/MIS Equipments/K-YAN | DPMU | 2.32 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-8(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 2.64 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-8(e) | Other office equipments for 4 PFT offices | DPMU | 1.46 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Tonk |  | 10.97
| G-9 | DPMU Kota
| G-9(a) | Furniture and fixture for 4 pfts(remaining) | DPMU | 1.88 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-9(b) | Other office equipments/K-YAN | DPMU | 2.23 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Kota |  | 4.11
| G-10 | DPMU Jhalawar
| G-10(a) | Other office equipments/K-YAN | DPMU | 1.27 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-10(b) | Furniture and fixture for 4 pfts | DPMU | 2.64 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-10(c) | Other office equipments | DPMU | 1.46 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Jhalawar |  | 5.37
| G-11 | DPMU Bhilwara
| G-11(a) | Furniture and Fixtures | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-11(b) | Other Office equipments | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-11(c) | IT/MIS Equipments/K-YAN | DPMU | 0.77 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-11(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-11(e) | Other office equipments for 4 PFT offices | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Bhilwara |  | 0.77
| G-12 | DPMU Rajsamand
| G-12(a) | Furniture and Fixtures | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-12(b) | Other Office equipments | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-12(c) | IT/MIS Equipments/K-YAN | DPMU | 0.77 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-12(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 2.64 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-12(e) | Other office equipments for 4 PFT offices | DPMU | 1.46 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Rajsamand |  | 4.87
| G-13 | DPMU Dungarpur
| G-13(a) | Furniture and Fixtures | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-13(b) | Other Office equipments | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-13(c) | IT/MIS Equipments/K-YAN | DPMU | 0.77 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-13(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-13(e) | Other office equipments for 4 PFT offices | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Dungarpur |  | 0.77
| G-14 | DPMU Dausa
| G-14(a) | Furniture and Fixtures | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-14(b) | Other Office equipments | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-14(c) | IT/MIS Equipments/K-YAN | DPMU | 0.77 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-14(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-14(e) | Other office equipments for 4 PFT offices | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Dausa |  | 0.77
| G-15 | DPMU Banswara
| G-15(a) | Furniture and Fixtures | DPMU | 2.73 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-15(b) | Other Office equipments | DPMU | 2.52 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-15(c) | IT/MIS Equipments/K-YAN | DPMU | 2.2 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-15(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 2.64 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-15(e) | Other office equipments for 4 PFT offices | DPMU | 1.48 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
|  | TOTAL DPMU & PFT Banswara |  | 11.57
| G-16 | DPMU Dholpur
| G-16(a) | Furniture and Fixtures | DPMU | 2.73 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-16(b) | Other Office equipments | DPMU | 2.44 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-16(c) | IT/MIS Equipments/K-YAN | DPMU | 2.97 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-16(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 0.66 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-16(e) | Other office equipments for 4 PFT offices | DPMU | 0.37 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Dholpur |  | 9.17
| G-17 | DPMU Sawaimadhopur
| G-17(a) | Furniture and Fixtures | DPMU | 1.8 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-17(b) | Other Office equipments | DPMU | 1.6 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-17(c) | IT/MIS Equipments/K-YAN | DPMU | 2.17 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-17(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 1.98 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-17(e) | Other office equipments for 4 PFT offices | DPMU | 1.1 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Sawaimadhopur |  | 8.65
| G-18 | DPMU Chittorgarh
| G-18(a) | Furniture and Fixtures | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-18(b) | Other Office equipments | DPMU | 1.65 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-18(c) | IT/MIS Equipments/K-YAN | DPMU | 0.77 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-18(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 1.32 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-18(e) | Other office equipments for 4 PFT offices | DPMU | 0.73 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Chittorgarh |  | 4.47
| G-19 | DPMU Bundi
| G-19(a) | Furniture and Fixtures | DPMU | 2.73 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-19(b) | Other Office equipments | DPMU | 2.52 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-19(c) | IT/MIS Equipments/K-YAN | DPMU | 2.2 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-19(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 2.64 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-19(e) | Other office equipments for 4 PFT offices | DPMU | 1.48 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
|  | TOTAL DPMU & PFT Bundi |  | 11.57
| G-20 | DPMU Pratapgarh
| G-20(a) | Furniture and Fixtures | DPMU | 2.73 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-20(b) | Other Office equipments | DPMU | 2.52 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-20(c) | IT/MIS Equipments/K-YAN | DPMU | 2.2 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-20(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 2.64 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-20(e) | Other office equipments for 4 PFT offices | DPMU | 1.48 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
|  | TOTAL DPMU & PFT Pratapgarh |  | 11.57
| G-21 | DPMU Karoli
| G-21(a) | Furniture and Fixtures | DPMU | 2.73 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-21(b) | Other Office equipments | DPMU | 2.52 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-21(c) | IT/MIS Equipments/K-YAN | DPMU | 2.2 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-21(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 2.64 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
| G-21(e) | Other office equipments for 4 PFT offices | DPMU | 1.48 | Shopping | 01.01.2014 | Post | 15.01.2014 | 25.01.2014 | NA | 30.01.2014 | 14.02.2014 | 20.02.2014 | NA
|  | TOTAL DPMU & PFT Karoli |  | 11.57
| G-22 | DPMU Bikaner
| G-22(a) | Furniture and Fixtures | DPMU | 2.6 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-22(b) | Other Office equipments | DPMU | 2.52 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-22(c) | IT/MIS Equipments/K-YAN | DPMU | 2.62 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-22(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 1.98 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-22(e) | Other office equipments for 4 PFT offices | DPMU | 1.1 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Bikaner |  | 10.82
| G-23 | DPMU Udaipur
| G-23(a) | Furniture and Fixtures | DPMU | 2.73 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-23(b) | Other Office equipments | DPMU | 2.34 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-23(c) | IT/MIS Equipments/K-YAN | DPMU | 1.62 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-23(d) | Furniture and Fixtures for 4 PFT office in the district | DPMU | 2.64 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
| G-23(e) | Other office equipments for 4 PFT offices | DPMU | 0 | Shopping | 01.10.2013 | Post | 15.10.2013 | 25.10.2013 | NA | 30.10.2013 | 16.11.2013 | 20.11.2013 | NA
|  | TOTAL DPMU & PFT Udaipur |  | 9.33
|  | TOTAL SPMU Works/Goods |  | 163.44
|  | TOTAL DPMU & PFT Goods |  | 137.29
|  | GRAND TOTAL |  | 300.73