|  |
| --- |
| 77801v. 2**Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 04/30/2013 |

|  |
| --- |
| **1. Basic Information** |
| Project ID & Name | P125105: PK:Flood Emergency Cash Transfer Project |
| Country | Pakistan |
| Task Team Leader | Kelly Johnson |
| Sector Manager/Director | Pablo Gottret |
| Country Director | Rachid Benmessaoud |
| Original Board Approval Date | 03/29/2011 |
| Original Closing Date: | 06/30/2013 |
| Current Closing Date | 06/30/2013 |
| Proposed Closing Date [if applicable] | 03/31/2014 |
| EA Category | C-Not Required |
| Revised EA Category | C-Not Required-Not Required |
| EA Completion Date |  |
| Revised EA Completion Date |  |

|  |
| --- |
| **2. Revised Financing Plan (US$m)** |
| **Source** | **Original** | **Revised** |
|  AID | 190.00 | 190.00 |
|  BORR | 100.00 | 100.00 |
|  DFID | 100.00 | 100.00 |
|  GITA | 65.00 | 65.00 |
|  IDA | 125.00 | 125.00 |
|  **Total** | 580.00 | 580.00 |

|  |
| --- |
| **3. Borrower** |
| **Organization** | **Department** | **Location** |
|  Islamic Republic of Pakistan |  | Pakistan |

|  |
| --- |
| **4. Implementing Agency** |
| **Organization** | **Department** | **Location** |
|  Cabinet Division |  | Pakistan |

|  |
| --- |
| **5. Disbursement Estimates (US$m)** |
| **Actual amount disbursed as of 05/20/2013** **122.43** |
| **Fiscal Year** | **Annual** | **Cumulative** |
|  2013 | 2.57 | 125.00 |
|   | **Total** | **125.00** |

|  |
| --- |
| **6. Policy Exceptions and Safeguard Policies** |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes****Original/Current Project Development Objectives/Outcomes** |
| Original: The development objective of the project is to support the recovery of flood affected households by assisting the Government of Pakistan (GoP) in strengthening the implementation of its Citizen’s Damage Compensation Program (CDCP).  |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|   |