|  |
| --- |
| 65654 v2**Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 12/15/2011 |

|  |
| --- |
| **1. Basic Information** |
| Project ID & Name | P082429: CO-(APL1)Disaster VulnerabilityReduction |
| Country | Colombia |
| Task Team Leader | Niels B. Holm-Nielsen |
| Sector Manager/Director | Guang Zhe Chen |
| Country Director | Gloria M. Grandolini |
| Original Board Approval Date | 05/10/2005 |
| Original Closing Date: | 12/31/2011 |
| Current Closing Date | 08/31/2013 |
| Proposed Closing Date [if applicable] | 08/30/2013 |
| EA Category | C-Not Required |
| Revised EA Category | C-Not Required-Not Required |
| EA Completion Date | 05/20/2004 |
| Revised EA Completion Date |  |

|  |
| --- |
| **2. Revised Financing Plan (US$m)** |
| **Source** | **Original** | **Revised** |
|  BORR | 141.00 | 141.00 |
|  IBRD | 260.00 | 110.00 |
|  **Total** | 401.00 | 251.00 |

|  |
| --- |
| **3. Borrower** |
| **Organization** | **Department** | **Location** |

|  |
| --- |
| **4. Implementing Agency** |
| **Organization** | **Department** | **Location** |
|  Ministry of Finance and Public Credit |  | Colombia |
|  Ministry of Environment, Housing and Territorial Development |  | Colombia |

|  |
| --- |
| **5. Disbursement Estimates (US$m)** |
| **Actual amount disbursed as of 03/29/2012** **89.77** |
| **Fiscal Year** | **Annual** | **Cumulative** |
|  2011 | 3.10 | 92.87 |
|  2012 | 5.30 | 98.17 |
|  2013 | 3.15 | 101.32 |
|   | **Total** | **101.32** |

|  |
| --- |
| **6. Policy Exceptions and Safeguard Policies** |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes****Original/Current Project Development Objectives/Outcomes** |
| The project's development objective is to strengthen national and local disaster risk management capacity.  |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|   |